## Sheet1
AADHAR BASED VOTING SYSTEM

MONTH	TASK NO.	1					2					3					4

MAY	1					Think about scope of improvement and Prepare a detailed abstract .
	2					Prepare a block diagram and think about the components.
	3
	4
JUNE	1	Finalize the components, make budget and prepare the circuit diagram
	2					Simulate the circuit (use proteus)
	3					Complete the simulation of the project.
	4
JULY	1	Obtain bread board level output
	2					Obtain o/p of various modules using Raspberry Pi
	3
	4
AUGUST	1	Design Product Structure
	2					Fabricate the PCB, Final touches, Incorporate various Aesthetic features etc.
	3
	4
SEPTEMBER	1	Display completed project for Excel 2k14
	2