## Sheet1
AADHAR BASED VOTING SYSTEM
MONTH | TASK NO. | 1 | 2 |  | 3 |  |  | 4
MAY | 1 |  |  |  | Think about scope of improvement and Prepare a detailed abstract .
| 2 | [6 empty] | Prepare a block diagram and think about the components.
3
4
JUNE | 1 | Finalize the components, make budget and prepare the circuit diagram
| 2 |  | Simulate the circuit (use proteus)
| 3 |  |  |  |  | Complete the simulation of the project.
4
JULY | 1 | Obtain bread board level output
| 2 | [5 empty] | Obtain o/p of various modules using Raspberry Pi
3
4
AUGUST | 1 | Design Product Structure
| 2 |  |  | Fabricate the PCB, Final touches, Incorporate various Aesthetic features etc.
3
4
SEPTEMBER | 1 | Display completed project for Excel 2k14
2